Clark National Sourcing Project Debrief

- Team Members:

- Kelly Campbell, Manager

- Karin Nicholas, Consultant

- Julie Appiah, Consultant

- Abby Rubin, AC

- Robin Miller, AC

- Situation:

- The Foundation’s new approach to grantmaking, entitled Institution and Field Building, is designed to strengthen youth development organizations that serve youth in non-school hours.  This strategy aims to help a number of youth serving organizations to improve the quality of their services and to serve more youth.  Pursuant to their strategy, the Foundation has outlined four youth-focused outcomes it hopes to achieve:  better educational skills, reduction in negative social behavior, better potential to earn a living, and civic engagement.  The Foundation, using a rigorous set of criteria, would like to surface a number of high potential youth development organizations that have already demonstrated effectiveness in achieving one or more of these outcomes.

- The Foundation has outlined a multi-stage process for implementing their strategy:  surfacing organizations, conducting due diligence on potential grantees, undertaking business planning for high potential organizations, making investments, and completing performance tracking and evaluations.

- This specific Bridgespan engagement was a three month case designed to assist the Foundation in surfacing organizations as well as understanding the city context in five Metropolitan Service Areas (MSA’s): Atlanta, San Francisco, Oakland, Los Angeles, and San Diego.  Bridgespan was one of a number of external consultants exploring cities across the country.  The effort was coordinated by an independent consultant, Clifford Pearlman.

- The team conducted interviews with “informants” (generally funders, independent consultants, and other intermediaries) to surface organizations, and then conducted secondary research on organizations in order to evaluate them against Clark’s funding criteria.

- Complication:

- The Foundation has traditionally funded organizations in the Northeast portion of the United States.  To date, the Foundation has not identified a substantial number of youth serving organizations that meet its goals and fit its criteria.

Critical Questions:

- Can the Foundation successfully implement its Institution and Field Building strategy by funding organizations outside of its traditional catchment area?

- Is there a pipeline of a significant number of organizations that meet the Foundation’s outcome goals and fit its criteria in other parts of the country?

Bridgespan Analyses:

- Sourcing

  - Database creation

  - Third party, youth development expert interviews

  - Secondary research

- Key Learnings:

- The team believes that the criteria and outcomes outlined in the Institution and Field Building Strategy will produce a pipeline of high potential youth development organizations in other MSA’s in the country.  While a number of candidates for due diligence were found in each city, our results suggest that the San Francisco MSA, perhaps combined with the Oakland/East Bay, has the highest potential to produce organizations that the Foundation would consider taking through due diligence.

- Overall, the team found that youth development organizations in all of the MSA’s operate in fragmented funding environments, contend with a multitude of issues, and employ a variety of approaches.   The San Francisco, and to some extent Oakland/East Bay MSA’s appeared to be on the cutting edge of youth development, employing new techniques and approaches before other areas.  High-level trends include: youth empowerment, voice and advocacy as well as a move toward a systemic integration of services (youth-centered but involving family/community).  The Los Angeles MSA shared many of the trends of the San Francisco Bay Area.  Los Angeles, however, was consistently described as a far more complex environment due to a number of drivers including great geographic distances, poor public transportation, and an extremely large, highly fragmented population.

- San Diego was unique with a citywide, government-funded after-school initiative for elementary and middle school youth.   In cities like Atlanta and San Diego, virtually every compelling organization surfaced has a budget size below Clark’s $500K minimum criteria.   While it is still difficult for these smaller organizations to get operating support, some foundations are trying to increase the organizational capacity and leadership capabilities of smaller organizations with capacity-building grants and nonprofit executive development programs, e.g.Eureka Fellowships, Fieldstone Foundation and Jacobs Foundation Center for Innovative Nonprofit Organizations (see San Diego Executive Summary).  Additionally, an unusually strong cluster of arts/media-based youth-development organizations has surfaced in Atlanta, and a number of innovative arts-based groups were found in cities like Milwaukee, Chicago and San Francisco (see individual city reports for more on city-specific trends and reports on top candidates for due diligence).

- Summary of Results by MSA:

- San Francisco

- The San Francisco MSA was expanded to include the Peninsula and the North Bay.  The counties covered include San Francisco (main emphasis), Marin, San Mateo, and Santa Clara.

- The team conducted twenty-three interviews in San Francisco.  Informants in the East Bay also provided information about San Francisco.

- A total of 84 organizations were surfaced in San Francisco and on the Peninsula.

- Oakland/East Bay

- The Oakland/East Bay MSA was expanded to include the counties of Alameda and Contra Costa.

- The team conducted eight interviews in Oakland/East Bay.  Many informants in San Francisco also provided information about Oakland/East Bay.

- A total of 32 organizations were surfaced in Oakland/East Bay.

- Los Angeles

- The Los Angeles MSA focused on Los Angeles County with further inquiries made into Ventura, Orange, Riverside, and San Bernardino Counties.

- The team conducted nineteen interviews in the Los Angeles area.

- A total of 66 organizations were surfaced in the Los Angeles area.

- San Diego

- The team conducted fourteen primary interviews in San Diego.

- A total of 36 organizations were surfaced in San Diego.

- Atlanta

- The team conducted eleven primary interviews in Atlanta.

- A total of 31 organizations were surfaced in Atlanta.

- What we would do differently?

  - The Bridgespan approach to exploring each MSA provided rich insights, comprehensive organization information, and a number of helpful contacts in each city.  Some of our success in getting to detailed organizational information and surfacing candidates for due diligence that ‘fit’ with Clark criteria could be attributed to:

- Careful understanding of Clark’s criteria – other independent consultants without our history of working with Clark did not have the ‘tacit’ knowledge of which organizations were in/ which were out of scope of Clark’s criteria.  Evaluation was an art, not a science, and involved a lot of team discussion on the case-by-case specifics.

- Deeper probing on organizations through cross-referencing interviews.  Once we had determined the organization fit with Clark’s descriptive criteria (budget size, scope, etc) we tried to develop a point of view on how it fit with their due diligence criteria –especially regarding how compelling the model, the outcomes focus and the  leadership/management team

  - A key learning, related to the first point above, is that it is difficult to evaluate organizational effectiveness on paper.  This process can be facilitated by clarifying expectations around an organization’s  ‘demonstrated effectiveness’ in each of the due diligence criteria areas.  To that end, it may be useful to have a kickoff meeting discussing the due diligence questions Clark asks along each of the criteria, (the ‘red flag analysis’ or ‘due diligence indicators’) and clarifying their relative priority vis-à-vis one another.

  - Given time constraints, the decision to conduct the majority of interviews by phone was correct.  If additional resources and/or time were available, more interviews should be conducted in person as personal interviews often resulted in superior information and written materials provided by the informant.

  - While the teams’ approach used a variety of useful resources, the NCCS database was not used.  In the future, teams may consider using this as an effective resource to review the city landscapes and to understand the number of organizations that would have fit into Clark’s criteria.

  - Lastly, under more ideal circumstances, the Bridgespan team would be staffed out of one office.  Given the calibration and refinement required across the teams, having the team located in one office, or perhaps having periodic in-person meetings, would have been helpful.  The trade-off is the physical proximity to the cities explored and the associated in-person option and time zone benefits.