## Sheet1
Construction Schedule
West Gate High Rise Common Areas Sprinkler & Fire Alarm
Building | Unit | Start | Complete
W85 High-rise | Sub Basement | 2006-02-27 | 2006-03-03
W85 High-rise | Basement | 2006-03-06 | 2006-04-04
W85 High-rise | First Floor Lobby | 2006-03-20 | 2006-04-04
W85 High-rise | Mezzanine | 2006-03-13 | 2006-03-17
W85 High-rise | Play Room | 2006-04-10 | 2006-04-14
W85 High-rise | Mailboxes | TBD | TBD
W85 High-rise | Electric Closets on Flrs. 2 thru 18 | 2006-02-28 | 2006-03-10
W85 High-rise | 1st Fire Alarm Testing | TBD | TBD
W85 High-rise | 2nd Fire Alarm Testing | TBD | TBD
Note: Hours of operation 8 am. To 4pm.
No noisy work until 9 am.
4 pm. To 6 pm. Clean up