## Sheet1
Construction Schedule
West Gate High Rise Sprinkler & Fire Alarm
Building | Unit | Start | Complete
W85 High-rise | 2nd and 3rd Floor Hallway Work | 2006-03-27 | 2006-03-31
W85 High-rise | 4th and 5th Floor Hallway Work | 2006-03-31 | 2006-04-07
W85 High-rise | 6th and 7th Floor Hallway Work | 2006-03-31 | 2006-04-07
W85 High-rise | 8th and 9th Floor Hallway Work | 2006-04-07 | 2006-04-14
W85 High-rise | 10th and 11th Floor Hallway Work | 2006-04-07 | 2006-04-14
W85 High-rise | 12th and 13th Floor Hallway Work | 2006-04-14 | 2006-04-24
W85 High-rise | 14th and 15th Floor Hallway Work | 2006-04-14 | 2006-04-24
W85 High-rise | 16th Floor Hallway Work | 2006-04-24 | 2006-04-26
W85 High-rise | 201, 202, 203, 204, & 205 | 2006-04-03 | 2006-04-03
W85 High-rise | 206, 207, 208, 209, & 210 | 2006-04-04 | 2006-04-04
W85 High-rise | 301, 302, 303, 304, & 305 | 2006-04-05 | 2006-04-05
W85 High-rise | 306, 307, 308, 309, & 310 | 2006-04-05 | 2006-04-05
W85 High-rise | 401, 402, 403, 404, & 405 | 2006-04-07 | 2006-04-07
W85 High-rise | 406, 407, 408, 409, & 410 | 2006-04-10 | 2006-04-10
W85 High-rise | 501, 502, 503, 504, & 505 | 2006-04-11 | 2006-04-11
W85 High-rise | 506, 507, 508, 509, & 510 | 2006-04-12 | 2006-04-12
W85 High-rise | 601, 602, 603, 604, & 605 | 2006-04-13 | 2006-04-13
W85 High-rise | 606, 607, 608, 609, & 610 | 2006-04-14 | 2006-04-14
W85 High-rise | 701, 702, 703, 704, & 705 | 2006-04-18 | 2006-04-18
W85 High-rise | 706, 707, 708, 709, & 710 | 2006-04-19 | 2006-04-19
W85 High-rise | 801, 802, 803, 804, & 805 | 2006-04-20 | 2006-04-20
W85 High-rise | 806, 807, 808, 809, & 810 | 2006-04-21 | 2006-04-21
W85 High-rise | 901, 902, 903, 904, & 905 | 2006-04-24 | 2006-04-24
W85 High-rise | 906, 907, 908, 909, & 910 | 2006-04-25 | 2006-04-25
W85 High-rise | 1001, 1002, 1003, 1004, & 1005 | 2006-04-26 | 2006-04-26
W85 High-rise | 1006, 1007, 1008, 1009, & 1010 | 2006-04-27 | 2006-04-27
W85 High-rise | 1101, 1102, 1103, 1104, & 1105 | 2006-04-28 | 2006-04-28
W85 High-rise | 1106, 1107, 1108, 1109, & 1110 | 2006-05-01 | 2006-05-01
W85 High-rise | 1201, 1202, 1203, 1204, & 1205 | 2006-05-02 | 2006-05-02
W85 High-rise | 1206, 1207, 1208, 1209, & 1210 | 2006-05-03 | 2006-05-03
W85 High-rise | 1301, 1302, 1303, 1304, & 1305 | 2006-05-04 | 2006-05-04
W85 High-rise | 1306, 1307, 1308, 1309, & 1310 | 2006-05-05 | 2006-05-05
W85 High-rise | 1401, 1402, 1403, 1404, & 1405 | 2006-05-08 | 2006-05-08
W85 High-rise | 1406, 1407, 1408, 1409, & 1410 | 2006-05-09 | 2006-05-09
W85 High-rise | 1501, 1502, 1503, 1504, & 1505 | 2006-05-10 | 2006-05-10
W85 High-rise | 1506, 1507, 1508, 1509, & 1510 | 2006-05-11 | 2006-05-11
W85 High-rise | 1601, 1602, 1603, 1604, & 1605 | 2006-05-12 | 2006-05-12
W85 High-rise | 1606, 1607, 1608, 1609, & 1610 | 2006-05-15 | 2006-05-15
W85 High-rise | Fire Alarm Testing | TBD | TBD
Note: Hours of operation 8 am. To 4pm.
No noisy work until 9 am.
4 pm. To 6 pm. Clean up